## Gamsabha
Moonshot — Gamsabha
Description | Responsibility | Department | Category | Days | 2026-06-02 18:30 | 2026-06-03 18:30 | 2026-06-04 18:30 | 2026-06-05 18:30 | 2026-06-06 18:30 | 2026-06-07 18:30 | 2026-06-08 18:30 | 2026-06-09 18:30 | 2026-06-10 18:30 | 2026-06-11 18:30 | 2026-06-12 18:30 | 2026-06-13 18:30 | 2026-06-14 18:30 | 2026-06-15 18:30 | 2026-06-16 18:30 | 2026-06-17 18:30 | 2026-06-18 18:30 | 2026-06-19 18:30 | 2026-06-20 18:30 | 2026-06-21 18:30
Temporary Partition Installation | Udara | Projects | Preparation & Temporary Setup | 13
Back area Civil and Plumbing works | Udara | Projects | Back Wall Work | 13
Back area Electrical works | Amaya | Projects | Back Wall Work | 13
Back area Networking related works | Mahen | IT | Back Wall Work | 13
Backwall fitouts (SS ¦ Furniture ¦ Graphics) | Nisal / Yohan | Projects | Back Wall Work | 13
Proposed Chicken area equipment placing and commission | Shamishka | Projects | Uncategorised | 13
Temporary Partition Removal | Udara/ Asanka/ Shasmishka/ Nisal/ Amaya/ Mahen | Projects | Preparation & Temporary Setup | 1
Fit out works (SS) - Juice & Bakery Modules | Nisal/ Amaya/ Udara/ Yohan/ Mahen | Projects | Juice & Bakery Fit-out | 2
Fit out works (Furniture & Graphics) - Juice & Bakery Modules | Nisal/ Amaya/ Udara/ Yohan/ Mahen | Projects | Juice & Bakery Fit-out | 2
Power supply for Juice & Bakery Modules | Nisal/ Amaya/ Udara/ Yohan/ Mahen | Projects | Juice & Bakery Fit-out | 2
IT, Network supply for the Infill+POS and TV - Juice & Bakery modules | Nisal/ Amaya/ Udara/ Yohan/ Mahen | IT | Juice & Bakery Fit-out | 2
Seating area arrangements (Furniture) | Nisal/ Amaya/ Udara/ Yohan/ Mahen | Projects | Uncategorised | 2
Setting up the back wall | Shamishka/ Amaya/ Mahen |  | Back Wall Work | 1
Final finishing and troubleshooting |  |  | Handover & Closeout | 3
Project Handing Over |  |  | Handover & Closeout | 1